## Sheet1
Marketing Task | Completion Date
Sign listing agreement | August 9th
Prepare and finalize the marketing package and gain owner approval | August 23th
Publish property website | August 30st
Begin Google Adwords campaign targeting people searching for retail shopping centers for sale in Orlando, FL | September 2nd
Begin first stage of email marketing campaign to internal database of principals and other brokers | September 5th
Cold call 50 selected principals with acquisition criteria that match property characteristics | September 10th
Publish listing on third-party websites - LoopNet, CCIM, MLS, TotalCommercial, craigslist, 42Floors, etc. | September 13th
Run an ad in the Orlando Sentinel | September 20th
Mail postcards to owners of similar properties within 100-mile radius | September 27th
Begin second stage of email marketing campaign to internal database of principals and other brokers | October 1st
Attend local ICSC marketing breakfast and present listing to the group | October 15th
Follow up on cold calls with Principals | October 17th
Publish listing to select LinkedIn and Google Plus property exchange groups | October 24th
Begin second stage of email marketing campaign to internal database of principals and other brokers | October 28th
Create LinkedIn and Facebook Ad Campaigns | November 1st
Attend local CCIM networking event and promote the listing with handouts | November 8th
Follow up on inquiries and requests for marketing packages | Ongoing
Cold call 50 owners per month of similar properties within 25 mile radius | Ongoing
Send owner progress report on marketing activity | Monthly